## Sheet1
SOU EITA Implementation Plan
Corrective Action Strategy
Central Recommendations:
Audit Findings / Suggested recommendations | Corrective Action Strategy | Planned Start Date | Planned Completion Date | Responsible Parties | Updates
Create a digital accessibility group | SOU will create an Accessiblity Task Force to promote Accessibility on Campus, and who will meet Quarterly to discuss any issues or suggestions to improve accessibility on campus | 2018-06-08 | 2019-01-01 | Accessibility Coordinator, Accessible Technology Specialist | Completed. Group consists of the following members: CIO, HR/Accessibility Coordinator, DR/Accessibile Technology Specialist, CFO, Asst. Provost, Director of Marketing, IT Programmer/Analyst, Library E-Resource/Systems web Coordinator/Assoc Professor
Create a central page for accessibility that links to other campus and non-campus resources. 1) Include upcoming training options 2) Include a monthly digitial accessibility tip | Accessibility Coordinator, Accessibility Technology Specialist will work with Information Technology to create a main accessibility page to provide accessibility policies, resources, links etc. | 2018-07-01 | 2018-11-01 | Accessibility Coordinator, Accessible Technology Specialist, designated person from IT | Completed.
Determine procedures for moving SOU toward desired digital accessibility goals | Create and Electronic and Information Technology Accessibility Policy and Procedure to outline policies and procedures which apply to SOU's commitment of accessibility | 2018-05-30 | 2020-07-14 | Accessibility Coordinator, Accessible Technology Specialist, IT, Accessibility Task Force | Completed. Electronic and Information Technology Accessibility Policy FAD.087 Approved 7/14/20 and the Accessibility and Selection of Instructional Materials Policy AAD.058 Approved 7/14/20
Make inclusive education a part of SOU job descriptions and merit pay. 1) Set up a recognition or "award" for one or two faculty who are exemplary in being accessible/inclusive and showcase that individual 2) Once a quarter highlight a digital accessibility champion | Human Resources will review job descriptions to include "preferrences" for "experience in designing courses, documents and other materials for accessibility, ensuring adequate access to information through assistive technologies." | 2018-07-01 | 2019-12-01 | Accessibility Coordinator, Human Resources | Completed -Class Comp Manager to incorporate into future job postings as appropriate. Accessibility Coordinator reviewing all new job postings to ensure physical demands are inclusive for those with disabilities.
Define a fundamental program alteration and stated process | 1. For EIT decisions, CIO (or designee) will collaborate with Assistive Technology Specialist to establish criteria for a fundamental program alteration process. 2. For non-EIT decisions, Disability Resources, Provost and Department Directors will establish what a fundamental program alteration would be and the process for which a decision is decided. | Winter 2019 | Fall 2019 | 1. CIO (or designee), Assistive Technology Specialist 2. DR, Provost, Department Directors
If time still allows, include a digital accessibility question in the CIO search | Search is closed | NA | NA | Accessibility questions were included in the search. Hired candidate has accessibility experience, having gone through similar process to ours at University of Montana. | Completed. Hired candidate has accessibility Experience
Information Technology:
Audit Findings / Suggested recommendations | Corrective Action Strategy | Planned Start Date | Planned Completion Date | Responsible Parties
Utilize Students with disabilities in IT Digital accessibility reviews | DR and IT will collaborate on a job description for student testers. DR will identify students with disabilities and present them with the opportunity to participate. Willing students would be hired as student workers by IT for this express purpose. | 2019-01-01 | 5/1/20 and continuing | IT, DR | Met with the Foundation to see if scholarships exist to attract disabled students that we could employ. Will work with Enrollment to see if we can more effectivley recurit disabled students. Strategy will be to work to implement students in the digital accessibility reviews
Create a process for testing SOU software products before procurement and during development on campus that follows NFB's browser recommendations for JAWS testing (Addressing the question of Edge), but which also utilizes NVDA, VoiceOver and Talkback, and which is updated annually to reflect changes in technology | DR will assist IT staff in learning to use various screenreaders for testing and/or will locate resources for obtaining that training outside of the university. IT will define processes and designate appropriate staff. | 2019-01-01 | 5/1/20 and continuing | IT, DR | Update contracts to include break of contract for inaccessibility
Standardize digital accessibility testing process for all IT Coordinators | SOU will incorporate this function into student testing and the procurement process, as above. | 2019-01-01 | 5/1/20 and continuing | IT
Add accessibility statements and tips to Knowledgebase articles | As the knowledgebase changes, all new entries will include accessibility statements and tips where appropriate. | 2019-01-01 | 5/1/20 and continuing | IT
Classrooms and Lecture Halls:
Audit Findings / Suggested recommendations | Corrective Action Strategy | Planned Start Date | Planned Completion Date | Responsible Parties
Consider supplementing touch screen podium access with iPads if controller brand allows | IT to review suggesstion and determine feasbility | Spring 2019 | Fall 2019 | IT | This is being considered. IT is looking at the possibility of doing holistic upgrades to many classrooms. If we are approved, we will incorporate accessible solutions into the new builds.
Provide an attached sheet of Braille and visual instructions for accessing a web-based description of the controller's physical buttons and the iPads options and options for immedite support (help desk monitored accessible chart perhaps) | IT to partner with Disability Resources to have instructions converted into Braille | Spring 2019 | Fall 2019 | DR, IT
Continue to consider lecture recording for campus | Will continue to review feasibility for lecture recording | Fall 2019 | 2020-05-01 | CIS, IT, Provost's office, DR
Engage discussion of moving to voice over IP System and slowly replacing FM assisted listening devices for campus | Will continue to review | 2019-01-01 | 2020-09-01 | DR, IT | This is also being considered and may be addressed in the next academic year as part of classroom upgrades (pending budget approval).
Cross Departmental Collaboration
Audit Findings / Suggested recommendations | Corrective Action Strategy | Planned Start Date | Planned Completion Date | Responsible Parties
Increase cross departmental collaboration. For example; the Alternative Formats/Assistive Technology coodinator in Disability Resources and the seven IT coordinators use different software to create document accessibility. | 1. These groups will meet to discuss benefits of Acrobat Pro vs. ABBYY repair on documents. Being able to have the strength of both of these software programs on difficult cases might be helpful. In some cases, outsourcing conversion of critical, high use, and complex documents to accessible versions may be necessary. - In negotiations currently for acquisition of ABBYY solution. 2. Web developers across the university are already meeting to discuss processes and a potential web governance policy and process. | Fall 2018 | 2019-07-01 | IT, DR | SOU acquired the ABBY Fine reader recognition/conversion server in March 2019 as a tool to remediate PDF's. IT currently conducting department training on this system.
Purchases
Audit Findings / Suggested recommendations | Corrective Action Strategy | Planned Start Date | Planned Completion Date | Responsible Parties
Consider potential purchases that make digital accessibility a "no-thought" process. 1) Ally 2) ABBYY Recognition server for library scanners and old archives | Review these products to determine feasibility and function. DR and CIS have already discussed use of Ally for Moodle content accessibility and strongly recommend its purchase. | Spring 2019 | Spring 2021 | IT, CIS, DR, Library, Budget/Finance for approval of any additional cost | SOU acquired the ABBY Fine reader recognition/conversion server in March 2019 as a tool to remediate PDF's. IT currently conducting department training on this system.
Moodle
Audit Findings / Suggested recommendations | Corrective Action Strategy | Planned Start Date | Planned Completion Date | Responsible Parties
Make a more concerned effort to replace older style forums used for announcements | This is currently happening and will be an ongoing continuing effort | Fall 2017 | 5/1/20 and continuing | CIS
Provide "open lab" sessions with Disability Resources, IT and ADA Coordinator for faculty from related disciplines so that faculty are supported in their digital accessibility changes and learn from discussions about other courses | SOU will establish Moodle Accessibility Training Quarterly for Faculty needing assistance in creating accessible courses. SOU will establish a one hour, Quarterly Accessibility Talk/Meeting for faculty/Staff to come and address any topics of accessibility, concerns or ideas they want to share | 2018-01-19 | 5/1/20 and continuing | DR, IT, CIS, Accessibility Coordinator | IT and Instructional Support are currently providing accessibility training for faculty and staff. This continues on a monthly basis. Quarterly accessibility talk/meetings for facutly and staff will be scheduled.
Web
Audit Findings / Suggested recommendations | Corrective Action Strategy | Planned Start Date | Planned Completion Date | Responsible Parties
Include more campus web sites in SiteImprove Reviews | IT and Marketing will review to determine which sites are not currently reviewed by SiteImprove and implement a plan to ensure all web pages are monitored by SiteImprove | Fall 2018 | 5/1/20 and continuing | IT, Marketing, Budget/Finance for approval of any additional cost | IT recently expanded SOU Site-Improve license to cover an additional 2500 pages (from 5,000 -7,500) for review by SiteImprove.
Make sure that SiteImprove is scanning for inacessible PDFs on all sites | SiteImprove currently scans for inacessible PDFs on sites currently reviewed. Will review (as above) to see if additional sites can be included | Fall 2017 | Fall 2017 and continuing | IT, Budget/Finance for approval of any additional cost | IT recently expanded SOU Site-Improve license to cover an additional 2500 pages (from 5,000 -7,500) for review by SiteImprove.
Focus campus on moving from document forms to web forms. Standardize to one or two web form applications | IT will continue to review and add an initiative to its planning process for initiatives beginning in FY 19-20 | Fall 2017 | 2020-05-01 | IT, web developers | IT is releasing a new strategic plan where this effort will be listed as an initiative. Much work has already begun in the HR department on this front.
Create procedures so videos without captions or audio descriptions do not get posted on sou.edu or inside.sou.edu | 1. SOU will establish a web governance policy for posting of documents and videos on webpages. This may include limiting the number of web adminsitrators, or require review by IT before something is allowed to "go live" on the webpage. 2. The DMC is engaging an automated captioning process for all of their streamed content, including SOU content. DMC and DR will collaborate on a process to review and improve captions to DCMP standards for instructional material used more than once, content designated for SOU website posting, and material in classes where students requesting accommodation are enrolled. | 2018-11-01 | 2019-07-01 | IT, DR, Accessibility Coordinator, Accessibility Task Force, Digital Media Center | As part of the oversight for inside.sou.edu, IT has been directing video posters to rev.com to have videos captioned before being posted. This effort began in April of 2019.
Add a link to the central accessibility page in the footer of campus templates and a statement about assistance available if something is inaccessible | SOU will add a link to campus templates and a statement about assistance avaialble if something is inaccessible | Fall 2019 | Completed prior to 10/1/2018 | IT
Require a very short qualifying test every year for individuals with editing access to campus web pages - inlcude study materials and focus one of the questions on accessibility | Schedule for discussion in Web Governance Group for inclusion in policy development | Fall 2019 | Fall 2019 and continuing | Web Governance Group, Policy Council, Cabinet | IT is working with the VP of Admissions, Enrollment SA to centralize governance through IT where accessibility training can be enforced.
Teach only accessible techniques when teaching about the website 1) Always mention that documents and other website attachments need to be accessible 2) Describe the characteristics of good alt tags and why appropriate use of headers is helpful | IT and Disability Resources are currently meeting this standard. | Fall 2017 | Fall 2017 and continuing | IT
Have a plan to incorporate accessibility comments into all training- rather than having it only mentioned in accessibility training | IT and Disability Resources will work to introduce accessibility comments into training where appropriate. | Fall 2017 | Fall 2017 and continuing | IT, CIS
Emergency Procedures
Audit Findings / Suggested recommendations | Corrective Action Strategy | Planned Start Date | Planned Completion Date | Responsible Parties
Digital signage can be integrated with emergency systems and can provide audio to student smart phones and hand held devices based on proximity to the sign. This kind of integration and signage can improve accessibility to campus information that is normally not seen by some students | SOU's alert system already incorporates emergency notifications in email, phone, and text alerts. Digital signage inclusion will be discussed with the various stakeholders on campus currently using digital signage. - SOU Alerts already provides alerts via personal cell phones, with accessibility set by students via personal mobile device. | Fall 2017 | Fall 2017 | IT, digital signage stakeholders on campus (SU, SRC, Business) | alert us - audio and visual alerts
Some SOU webpages are coordinated with emergency systems. There should be campus level discussion on whether all campus websites are similarily coordinated | SOU Alert placed on SOU webpages coordinated with alert system. | Fall 2017 | Fall 2017 | Accessibility Coordinator, Accessible Technology Specialist, IT, Accessibility Task Force